## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
7Iq3yVS2k0WFJrSxS8EjtMkAGw3l | Prepare methodology section | Proposal Phase (July – September 2025) | started | Medium | SEWWANDI C.I it22609526 | SEWWANDI C.I it22609526 | 06/03/2026 | 10/08/2025 | 2025-08-14 | false | true | 2025-08-14 | SEWWANDI C.I it22609526
BOlwZ4UoUUigpKZQV9wElckAGzfu | Conduct detailed literature review | Proposal Phase (July – September 2025) | started | Medium | SEWWANDI C.I it22609526 | SEWWANDI C.I it22609526 | 06/03/2026 | 24/07/2025 | 2025-08-05 | false | true | 2025-08-05 | SEWWANDI C.I it22609526
K3-8LVEJzEW4m-ZMQRcMyskACO2M | Start Drafting Final Research Report | Final Report & Viva (March – April 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334 | SEWWANDI C.I it22609526 | 2026-03-07 | 2026-03-09 | 2026-04-06 | false | false | 2026-03-09 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334 |  |  |  | Introduction Literature Review Methodology Implementation Results Conclusion
SIJkoaBlhUO_KUYOSCuF08kAPBOs | Prepare comparison study table | Proposal Phase (July – September 2025) | started | Medium | SEWWANDI C.I it22609526 | SEWWANDI C.I it22609526 | 06/03/2026 | 12/08/2025 | 2025-08-14 | false | true | 2025-08-14 | SEWWANDI C.I it22609526
TQePBfhHyEWSjC60_r3gpMkANmpJ | Draft research paper structure | Research Paper & Logbook (April – May 2026) | started | Medium | SEWWANDI C.I it22609526;DILSHAN G H A C it22581334;ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609526 | 07/03/2026 | 05/01/2026 | 2026-03-06 | false | true | 2026-03-06 | SEWWANDI C.I it22609526;DILSHAN G H A C it22581334;ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358
XzbfpqS5pU2AHbUK0yz6E8kAKM5T | Write full proposal report draft | Proposal Phase (July – September 2025) | started | Medium | SEWWANDI C.I it22609526 | SEWWANDI C.I it22609526 | 06/03/2026 | 10/08/2025 | 2025-08-15 | false | true | 2025-08-15 | SEWWANDI C.I it22609526
fN9o15JA3E24RCf353Ti5ckAAj-- | Submit final proposal report | Proposal Phase (July – September 2025) | started | Medium | SEWWANDI C.I it22609526 | SEWWANDI C.I it22609526 | 2026-03-06 | 2026-03-10 | 2025-09-19 | false | true | 2025-09-19 | SEWWANDI C.I it22609526
rIKmUhcrcki-CCdpinRLsMkAA4DG | Write research paper | Research Paper & Logbook (April – May 2026) | started | Medium | ABEYSEKARA K.S it22605634;DILSHAN G H A C it22581334;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526 | SEWWANDI C.I it22609526 | 2026-03-07 | 2026-03-10 | 13/01/2026 | false | true | 2026-03-10 | ABEYSEKARA K.S it22605634;DILSHAN G H A C it22581334;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526 |  |  |  | ABSTRACT INTRODUCTION LITERATURE REVIEW METHODOLOGY RESULTS AND DISCUSSION CONCLUSION ACKNOWLEDGMENT
2tLk3xKAQEaQaIRqChpoXckAOOcv | Prepare prototype demonstration materials | Progress Presentation II (March 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334 | SEWWANDI C.I it22609526 | 08/03/2026 | 10/03/2026 | 10/03/2026 | false | true | 2026-03-10 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334
2jHRUpuLDUCJ4wiVWQsorMkAM_Kx | Submit research paper to conference | Research Paper & Logbook (April – May 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581335 | SEWWANDI C.I it22609526 | 07/03/2026 | 14/01/2026 | 14/01/2026 | false | true | 2026-03-10 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581335 |  |  |  | Conference: INTERNATIONAL RESEARCH CONFERENCE ON SMART COMPUTING AND SYSTEMS ENGINEERING 2026
Zk7_X4QpeEGjm_iwyB3P7ckAJVOJ | Revise paper based on feedback | Research Paper & Logbook (April – May 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581336 | SEWWANDI C.I it22609526 | 07/03/2026 | 13/01/2026 | 13/01/2026 | false | true | 2026-01-14 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581336
l3ks1XySGUKxOJV-dtK4uckAJ_HX | Internal review of paper with supervisor | Research Paper & Logbook (April – May 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581337 | SEWWANDI C.I it22609526 | 07/03/2026 | 13/01/2026 | 13/01/2026 | false | true | 2026-01-13 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581337
Tf_8mH0Ls0-1N8Zjg23TtMkAC-h1 | Identify research contribution for publication | Research Paper & Logbook (April – May 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581338 | SEWWANDI C.I it22609526 | 07/03/2026 | 13/01/2026 | 13/01/2026 | false | false | 2026-01-13 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581338
PR83NuMo8UK6D4Zs5WDWV8kAP0Qf | Select journal/conference for paper submission | Research Paper & Logbook (April – May 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581339 | SEWWANDI C.I it22609526 | 07/03/2026 | 13/01/2026 | 13/01/2026 | false | false | 2026-01-13 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581339
aGIE6AhFYkK4PYXLWyAyfskANcHn | Submit presentation documentation | Progress Presentation I (December 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581340 | SEWWANDI C.I it22609526 | 07/03/2026 | 09/01/2026 | 09/01/2026 | false | true | 2026-01-13 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581340
ai2EUzol2k-dijT1hb1BpckALz5l | Submit presentation documentation | Progress Presentation II (March 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581341 | SEWWANDI C.I it22609526 | 07/03/2026 | 10/03/2026 | 11/03/2026 | false | true | 09/01/2026 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581341
DyZ9F42UykCgbOq_NUcB3skAANFR | Conduct Progress presentation II | Progress Presentation II (March 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581342 | SEWWANDI C.I it22609526 | 07/03/2026 | 10/03/2026 | 10/03/2026 | false | true | 11/03/2026 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581342
nJjUbJdZ_kK1FHXohy_FY8kABowS | Update testing results for presentation | Progress Presentation II (March 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581343 | SEWWANDI C.I it22609526 | 07/03/2026 | 10/03/2026 | 10/03/2026 | false | false | 10/03/2026 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581343
9SlZuIZzCkiiVvyR-liZO8kADvuC | Prepare PP2 slides | Progress Presentation II (March 2026) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581344 | SEWWANDI C.I it22609526 | 07/03/2026 | 08/03/2026 | 10/03/2026 | false | true | 10/03/2026 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581344
RP-lIy74k0ex_shP2uCDlckAN_52 | Conduct progress presntation I | Progress Presentation I (December 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581345 | SEWWANDI C.I it22609526 | 07/03/2026 | 09/01/2026 | 09/01/2026 | false | true | 10/03/2026 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581345
2iBqdhwA9ECJi9in__2LtMkAGNiq | Prepare prototype demonstration materials | Progress Presentation I (December 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581346 | SEWWANDI C.I it22609526 | 07/03/2026 | 05/01/2026 | 07/01/2026 | false | true | 09/01/2026 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581346
hwDJGhmklUm2OS2E7_h7ickANXLV | Prepare PP1 slides | Progress Presentation I (December 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581347 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-02 | 06/01/2026 | false | true | 06/01/2026 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581347
kkB9Xy5s4UuburExT3tFkckAJB4H | Cost variance validation | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-15 | 2026-01-22 | false | false | 2026-01-22 | RAJAPAKSHA R.M.K.U it22565358 |  |  | Budget & Cost Forecasting
kGcGsGrNvEaxsw1g6Ja99ckAMsfU | Cost variance validation | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565359 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-15 | 2026-01-22 | false | false | 2026-01-22 | RAJAPAKSHA R.M.K.U it22565359 |  |  | Budget & Cost Forecasting
5QpkRnHD4k6O7Y5wvl8JNskAKhDO | Forecast accuracy evaluation | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565360 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-10 | 2026-01-18 | false | false | 2026-01-18 | RAJAPAKSHA R.M.K.U it22565360 |  |  | Budget & Cost Forecasting
gwg30UaAOU28QIS3xAthcskAGzeE | Visualization graphs generation | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565361 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-20 | 2025-12-30 | false | false | 2025-12-30 | RAJAPAKSHA R.M.K.U it22565361 |  |  | Budget & Cost Forecasting
v8Pka5XB3kCsY0snlPYj6skAGVQY | Alert for budget overrun | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565362 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-15 | 2025-12-25 | false | false | 2025-12-25 | RAJAPAKSHA R.M.K.U it22565362 |  |  | Budget & Cost Forecasting
vyqc5Gwh-kugM9ArCFUG1MkANW3K | Predictive forecasting model | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565363 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-05 | 2025-12-20 | false | false | 2025-12-20 | RAJAPAKSHA R.M.K.U it22565363 |  |  | Budget & Cost Forecasting
tB9C7snsCk6AzECuwrmwbskAM874 | Feed consumption analytics | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565364 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-02 | 2025-12-10 | false | false | 2025-12-10 | RAJAPAKSHA R.M.K.U it22565364 |  |  | Budget & Cost Forecasting
jCcQ0tWklEe3ofW77pJb-skAFSUa | Monthly expense summary logic | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565365 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-28 | 2025-12-08 | false | false | 2025-12-08 | RAJAPAKSHA R.M.K.U it22565365 |  |  | Budget & Cost Forecasting
EYzaeMDO1UOkPEbcOSWyN8kAJAp2 | Cost analytics dashboard | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565366 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-25 | 2025-12-05 | false | false | 2025-12-05 | RAJAPAKSHA R.M.K.U it22565366 |  |  | Budget & Cost Forecasting
YY7CbWmcMUWdviXEro6zmckADMSl | Expense entry module | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565367 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-20 | 2025-11-28 | false | false | 2025-11-28 | RAJAPAKSHA R.M.K.U it22565367 |  |  | Budget & Cost Forecasting
cO22e-2N0kWTiy6Bk2pRxckACt7N | Budget data structure design | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565368 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-15 | 2025-11-20 | false | false | 2025-11-20 | RAJAPAKSHA R.M.K.U it22565368 |  |  | Budget & Cost Forecasting
YAZfg2A5kUmRlKyfjdUbn8kABm3e | Expense category classification | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565369 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-12 | 2025-11-18 | false | false | 2025-11-18 | RAJAPAKSHA R.M.K.U it22565369 |  |  | Budget & Cost Forecasting
_27MxjCAEUiVQiFXBqe3YMkAMqdU | Live energy data storage | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609527 | 07/03/2026 | 2025-11-12 | 2025-11-19 | false | false | 2025-11-16 | RAJAPAKSHA R.M.K.U it22565370 |  |  | Budget & Cost Forecasting
Zp0j1sxORkqVUDLSUzX5EckAGT9p | Energy consumption cost calculation | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609528 | 07/03/2026 | 2025-11-12 | 2025-11-20 | false | false | 2025-11-17 | RAJAPAKSHA R.M.K.U it22565371 |  |  | Budget & Cost Forecasting
X73oooKICEGRajuwGeht8MkAP3ba | Multi-pond profit and loss comparison | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609529 | 07/03/2026 | 2025-11-12 | 2025-11-21 | false | false | 2025-11-18 | RAJAPAKSHA R.M.K.U it22565372 |  |  | Budget & Cost Forecasting
ShjcTnXTmU2cKwPanO9YKMkADtls | Inventory low stock alert | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609530 | 07/03/2026 | 2025-11-12 | 2025-11-22 | false | false | 2025-11-19 | RAJAPAKSHA R.M.K.U it22565373 |  |  | Budget & Cost Forecasting
UWJxXc1cGEGW9np-81vlXckAEtkM | Sensor replacement cost forecasting | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609531 | 07/03/2026 | 2025-11-12 | 2025-11-23 | false | false | 2025-11-20 | RAJAPAKSHA R.M.K.U it22565374 |  |  | Budget & Cost Forecasting
UNnZ0kqMcUa3_n5OrLmy48kAPnxo | Sensor anomaly correlation using ZMPT101B and ACS712 | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609532 | 07/03/2026 | 2025-11-12 | 2025-11-24 | false | false | 2025-11-21 | RAJAPAKSHA R.M.K.U it22565375 |  |  | Budget & Cost Forecasting
K2TNN7adoEK5RWli_4TtZMkANzUf | Historical energy cost trend analysis | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609533 | 07/03/2026 | 2025-11-12 | 2025-11-25 | false | false | 2025-11-22 | RAJAPAKSHA R.M.K.U it22565376 |  |  | Budget & Cost Forecasting
K8rMKGwvykCtcv7yNgq8sskAGbjo | Real-time budget monitoring | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609534 | 07/03/2026 | 2025-11-12 | 2025-11-26 | false | false | 2025-11-23 | RAJAPAKSHA R.M.K.U it22565377 |  |  | Budget & Cost Forecasting
gEv-Pqz2m0uOZWKOco-UXMkAMIVi | Pond-level expense tracking | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609535 | 07/03/2026 | 2025-11-12 | 2025-11-27 | false | false | 2025-11-24 | RAJAPAKSHA R.M.K.U it22565378 |  |  | Budget & Cost Forecasting
wbJ1lZR43UGiXphcu6MMFskAB_9F | Voltage and current spike detection using ZMPT101B and ACS712 | Implementation Phase (November 2025 – February 2026) | Not started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609536 | 07/03/2026 | 2025-11-12 | 2025-11-28 | false | false | 2025-11-25 | RAJAPAKSHA R.M.K.U it22565379 |  |  | Budget & Cost Forecasting
NJKvTy-KfUGXtbSoNcRotMkANVfK | Operational cost model design | Implementation Phase (November 2025 – February 2026) | started | Medium | RAJAPAKSHA R.M.K.U it22565370 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-10 | 2025-11-15 | false | false | 2025-11-15 | RAJAPAKSHA R.M.K.U it22565370 |  |  | Budget & Cost Forecasting
rq-jdeUX6k6eXNW_ZzLsuskAJVY9 | Maintenance reminder testing | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581334 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-28 | 2026-02-03 | false | false | 2026-02-03 | DILSHAN G H A C it22581334 |  |  | Water Quality Monitoring
pUdgU_WGnUa-A9N91DT_H8kAOzIH | Threshold alert validation | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581335 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-25 | 2026-01-30 | false | false | 2026-01-30 | DILSHAN G H A C it22581335 |  |  | Water Quality Monitoring
dxV84ELZaEeGfsFBv_oA6MkALZZA | Temperature accuracy test | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581336 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-20 | 2026-01-25 | false | false | 2026-01-25 | DILSHAN G H A C it22581336 |  |  | Water Quality Monitoring
cQ5CZEpYnkOoSvA4hhyevMkAA3AT | pH accuracy validation | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581337 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-18 | 2026-01-22 | false | false | 2026-01-22 | DILSHAN G H A C it22581337 |  |  | Water Quality Monitoring
WqlxZO15UUW4KVq4yXnO1skAGqdk | API sync with cloud database | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581338 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-10 | 2026-01-15 | false | false | 2026-01-15 | DILSHAN G H A C it22581338 |  |  | Water Quality Monitoring
tpqzJEOMe0CkggRQlSMpC8kANmCb | Connect water module to central alert system | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581339 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-05 | 2026-01-12 | false | false | 2026-01-12 | DILSHAN G H A C it22581339 |  |  | Water Quality Monitoring
fT8QNESzU0yIHnNyk3dvr8kAPW4K | Data logging module | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581340 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-28 | 2025-12-05 | false | false | 2025-12-05 | DILSHAN G H A C it22581340 |  |  | Water Quality Monitoring
lDtnlBWo8Eu0SVA6GaH62ckABBEn | Sensor anomaly detection | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581341 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-25 | 2025-12-03 | false | false | 2025-12-03 | DILSHAN G H A C it22581341 |  |  | Water Quality Monitoring
lr_aW7MqdkOX_hYvDRs-dckAByNJ | Periodic monitoring service | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581342 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-20 | 2025-11-28 | false | false | 2025-11-28 | DILSHAN G H A C it22581342 |  |  | Water Quality Monitoring
mxKsM-nfTEupOepmRkevFckAEg_5 | Maintenance reminder scheduler | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581343 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-18 | 2025-11-25 | false | false | 2025-11-25 | DILSHAN G H A C it22581343 |  |  | Water Quality Monitoring
8fi2Cf5uqkWK3XXhm-PLOMkAJx3f | Water parameter threshold logic | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581344 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-15 | 2025-11-20 | false | false | 2025-11-20 | DILSHAN G H A C it22581344 |  |  | Water Quality Monitoring
9R86lRtaO0SFYSTaZaivuMkALt0s | Sensor noise filtering setup | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581345 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-10 | 2025-11-15 | false | false | 2025-11-15 | DILSHAN G H A C it22581345 |  |  | Water Quality Monitoring
utlXS6itQEqPI_hZ7AmlBckABlUP | Temperature probe installation | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581346 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-08 | 2025-11-12 | false | false | 2025-11-12 | DILSHAN G H A C it22581346 |  |  | Water Quality Monitoring
VeBGxHnqXkejUz5_Wv2rnskAP4pP | pH sensor integration | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581347 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-05 | 2025-11-10 | false | false | 2025-11-10 | DILSHAN G H A C it22581347 |  |  | Water Quality Monitoring
LVZh0sVoIEiYhN9j2_i4VskAIzMU | Water quality sensor calibration | Implementation Phase (November 2025 – February 2026) | started | Medium | DILSHAN G H A C it22581348 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-01 | 2025-11-05 | false | false | 2025-11-05 | DILSHAN G H A C it22581348 |  |  | Water Quality Monitoring
apELzOopyUmEjeV__Xyj2skAKa73 | Prepare dataset for OpenCV / detection algorithm training | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609526 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-05 | 2025-12-12 | false | false | 2025-12-12 | SEWWANDI C.I it22609526 |  |  | Fish Mortality Detection & Environmental Alerts
hbp5AaFKzE-i16Vci86jgMkAPfll | Organize and label fish behavior dataset | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609527 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-01 | 2025-12-08 | false | false | 2025-12-08 | SEWWANDI C.I it22609527 |  |  | Fish Mortality Detection & Environmental Alerts
BnHbIYHIfEWYsL-hcFhV5MkAFzMS | Collect sample images of dead fish for mortality detection | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609528 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-25 | 2025-12-05 | false | false | 2025-12-05 | SEWWANDI C.I it22609528 |  |  | Fish Mortality Detection & Environmental Alerts
QbbmjJDI-kiEWuKJdQMFVskAMWja | Alert latency measurement | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609529 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-28 | 2026-02-03 | false | false | 2026-02-03 | SEWWANDI C.I it22609529 |  |  | Fish Mortality Detection & Environmental Alerts
0xQ7Z8dtxUqtB5fbkMIrXMkAFJOe | False positive reduction tuning | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609530 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-25 | 2026-01-30 | false | false | 2026-01-30 | SEWWANDI C.I it22609530 |  |  | Fish Mortality Detection & Environmental Alerts
82rQHZ9nWkKyRjzixwfHAMkAHfIS | Low-light IR testing | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609531 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-20 | 2026-01-25 | false | false | 2026-01-25 | SEWWANDI C.I it22609531 |  |  | Fish Mortality Detection & Environmental Alerts
gTPmSSc7JUOhgzpSYwSzI8kANMVP | Daylight detection testing | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609532 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-18 | 2026-01-22 | false | false | 2026-01-22 | SEWWANDI C.I it22609532 |  |  | Fish Mortality Detection & Environmental Alerts
D81ZUQJQMkCYkjaXBVEtQckAJS0V | Offline alert queue logic | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609533 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-08 | 2026-01-15 | false | false | 2026-01-15 | SEWWANDI C.I it22609533 |  |  | Fish Mortality Detection & Environmental Alerts
l08j-G8LGEOXy-n5BR9INckAMXEz | Firebase Cloud Messaging integration | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609534 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-02 | 2026-01-10 | false | false | 2026-01-10 | SEWWANDI C.I it22609534 |  |  | Fish Mortality Detection & Environmental Alerts
EwIlHvEldEW8RyhxpCcx38kAHsK4 | JSON event payload structure | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609535 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-22 | 2025-12-28 | false | false | 2025-12-28 | SEWWANDI C.I it22609535 |  |  | Fish Mortality Detection & Environmental Alerts
BIacPyEuM0aUfi3KDNnuOMkABuvc | Image crop evidence generation | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609536 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-18 | 2025-12-25 | false | false | 2025-12-25 | SEWWANDI C.I it22609536 |  |  | Fish Mortality Detection & Environmental Alerts
COF75DlGw0COCcr1ta4LsskABO0d | Alert cooldown mechanism | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609537 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-15 | 2025-12-22 | false | false | 2025-12-22 | SEWWANDI C.I it22609537 |  |  | Fish Mortality Detection & Environmental Alerts
RGK3iB07EkWgxepDw7J2ZckAHk3x | Rain-triggered alert tagging | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609538 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-10 | 2025-12-18 | false | false | 2025-12-18 | SEWWANDI C.I it22609538 |  |  | Fish Mortality Detection & Environmental Alerts
Q3S0_p74UEOZ7Q5_KtHXMskABHcE | Abnormal behaviour detection | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609539 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-05 | 2025-12-15 | false | false | 2025-12-15 | SEWWANDI C.I it22609539 |  |  | Fish Mortality Detection & Environmental Alerts
_DtDQ9F_qEevGtP7F1MuXskAJuWI | Mortality detection persistence logic | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609540 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-01 | 2025-12-10 | false | false | 2025-12-10 | SEWWANDI C.I it22609540 |  |  | Fish Mortality Detection & Environmental Alerts
lHNtEJ9QXUecLbAfUca3bskABAp1 | Background subtraction logic | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609541 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-25 | 2025-12-03 | false | false | 2025-12-03 | SEWWANDI C.I it22609541 |  |  | Fish Mortality Detection & Environmental Alerts
Afbjod6MKkS9KVB1HJlpCckAIux3 | OpenCV motion detection | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609542 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-18 | 2025-11-28 | false | false | 2025-11-28 | SEWWANDI C.I it22609542 |  |  | Fish Mortality Detection & Environmental Alerts
b3TeMeWs1EaNirqEfWN8sskAGIw2 | Waterproof enclosure design | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609543 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-14 | 2025-11-18 | false | false | 2025-11-18 | SEWWANDI C.I it22609543 |  |  | Fish Mortality Detection & Environmental Alerts
ZVSfGJrG6UaJq6MHxofaTckAMwZE | Waterproof enclosure design | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609544 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-14 | 2025-11-18 | false | false | 2025-11-18 | SEWWANDI C.I it22609544 |  |  | Fish Mortality Detection & Environmental Alerts
6XyugPJQTE6SSdVUWfDi_ckAFAWC | DHT22 configuration | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609545 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-10 | 2025-11-15 | false | false | 2025-11-15 | SEWWANDI C.I it22609545 |  |  | Fish Mortality Detection & Environmental Alerts
GBskVFHssk601CeN7_KfqckAIIgf | Rain sensor installation (YL-83) | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609546 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-08 | 2025-11-12 | false | false | 2025-11-12 | SEWWANDI C.I it22609546 |  |  | Fish Mortality Detection & Environmental Alerts
zPDPsS-yskGQUw0tHDlTR8kAOGbE | IR camera configuration | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609547 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-05 | 2025-11-10 | false | false | 2025-11-10 | SEWWANDI C.I it22609547 |  |  | Fish Mortality Detection & Environmental Alerts
3jorpTZyTE6XO06T_ViNe8kAKKHj | Raspberry Pi setup | Implementation Phase (November 2025 – February 2026) | started | Medium | SEWWANDI C.I it22609548 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-01 | 2025-11-05 | false | false | 2025-11-05 | SEWWANDI C.I it22609548 |  |  | Fish Mortality Detection & Environmental Alerts
v1hedRil-UCZdLm0SXI5GckAIX4I | Battery fail-safe validation | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605634 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-25 | 2026-01-30 | false | false | 2026-01-30 | ABEYSEKARA K.S it22605634 |  |  | Boat navigation & Automated feeding
caNchkCBtkWZglxBdCAMGskAIryE | Navigation accuracy testing | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605635 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-22 | 2026-01-28 | false | false | 2026-01-28 | ABEYSEKARA K.S it22605635 |  |  | Boat navigation & Automated feeding
UiPP-X2dnkKS0ewmjHrctskAJu3B | Closed-loop dosing accuracy test | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605636 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-18 | 2026-01-22 | false | false | 2026-01-22 | ABEYSEKARA K.S it22605636 |  |  | Boat navigation & Automated feeding
Hdh_3AKhD06AJJZho1VyKskAN66E | Even feed distribution validation | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605637 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-12 | 2026-01-18 | false | false | 2026-01-18 | ABEYSEKARA K.S it22605637 |  |  | Boat navigation & Automated feeding
33PeXQoo4keBGITXdExLkckAGfwB | API integration for remote feed scheduling | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605638 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-05 | 2026-01-10 | false | false | 2026-01-10 | ABEYSEKARA K.S it22605638 |  |  | Boat navigation & Automated feeding
H2fchKlpHUKHCckiGDm5gMkAKU_A | Connect feeding module with central database | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605639 | SEWWANDI C.I it22609526 | 07/03/2026 | 2026-01-02 | 2026-01-08 | false | false | 2026-01-08 | ABEYSEKARA K.S it22605639 |  |  | Boat navigation & Automated feeding
jc6JdLCWLk-DfMtobAENyskAEojx | Cloud sync for feeding logs | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605640 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-22 | 2025-12-30 | false | false | 2025-12-30 | ABEYSEKARA K.S it22605640 |  |  | Boat navigation & Automated feeding
UX19e-44GEGzdSZX5kRTlskACZqC | Jam detection & hopper empty detection | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605641 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-18 | 2025-12-24 | false | false | 2025-12-24 | ABEYSEKARA K.S it22605641 |  |  | Boat navigation & Automated feeding
HBXKLpZLDEGaj1Xz56YGeMkADpgD | Low battery detection logic | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605642 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-15 | 2025-12-20 | false | false | 2025-12-20 | ABEYSEKARA K.S it22605642 |  |  | Boat navigation & Automated feeding
0crKUzddvkeYCaWQn-1mgMkALlgz | Manual override control interface | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605643 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-10 | 2025-12-18 | false | false | 2025-12-18 | ABEYSEKARA K.S it22605643 |  |  | Boat navigation & Automated feeding
ZAP0E8PEhke9C74kbBq1V8kAFA-B | Boat navigation path algorithm | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605644 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-05 | 2025-12-15 | false | false | 2025-12-15 | ABEYSEKARA K.S it22605644 |  |  | Boat navigation & Automated feeding
MkYtGI4Y-U-cPgv6FcRE5ckAE8n8 | Weight-based feed dispensing logic | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605645 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-12-01 | 2025-12-08 | false | false | 2025-12-08 | ABEYSEKARA K.S it22605645 |  |  | Boat navigation & Automated feeding
| Feeding schedule algorithm | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605646 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-25 | 2025-12-02 | false | false | 2025-12-02 | ABEYSEKARA K.S it22605646 |  |  | Boat navigation & Automated feeding
jFeK7F8yPEeUpHWC8x22eMkACN39 | Solar power integration for boat | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605647 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-18 | 2025-11-25 | false | false | 2025-11-25 | ABEYSEKARA K.S it22605647 |  |  | Boat navigation & Automated feeding
HsTuDo1DLkC7S3SBQvG568kANdv0 | Feeding tray uniformity testing | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605648 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-14 | 2025-11-18 | false | false | 2025-11-18 | ABEYSEKARA K.S it22605648 |  |  | Boat navigation & Automated feeding
TXmQF8ckiUOMoPUudGqxPMkABMVb | Load cell calibration (5kg) | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605649 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-10 | 2025-11-15 | false | false | 2025-11-13 | ABEYSEKARA K.S it22605649 |  |  | Boat navigation & Automated feeding
uhhTsC4u00CL5GwiVakzfckAPdfP | Live feeding data storage using Load Cell and hopper level sensor into feeddb and weight_history | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605650 | SEWWANDI C.I it22609527 | 07/03/2026 | 2025-11-11 | 2025-11-16 | false | false | 2025-11-14 | ABEYSEKARA K.S it22605650 |  |  | Boat navigation & Automated feeding
gvKSL0__4U23PJKErFSm-skAPUn4 | Feed consumption calculation using Load Cell dispensed grams and feed price per kg | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605651 | SEWWANDI C.I it22609528 | 07/03/2026 | 2025-11-12 | 2025-11-17 | false | false | 2025-11-15 | ABEYSEKARA K.S it22605651 |  |  | Boat navigation & Automated feeding
Bhv8iYtJgkmr7uEcEPr5wskAHlwu | Feed inventory low stock alert using hopper level sensor percentage thresholds | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605652 | SEWWANDI C.I it22609529 | 07/03/2026 | 2025-11-13 | 2025-11-18 | false | false | 2025-11-16 | ABEYSEKARA K.S it22605652 |  |  | Boat navigation & Automated feeding
_EMycr1kRUO9N-wsP2m1zckAAY2s | Feed reorder forecasting using historical hopper depletion rate and supplier unit price | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605653 | SEWWANDI C.I it22609530 | 07/03/2026 | 2025-11-14 | 2025-11-19 | false | false | 2025-11-17 | ABEYSEKARA K.S it22605653 |  |  | Boat navigation & Automated feeding
GfJcKx2jfkmV3cgSjWFCockADKZG | Feeding anomaly correlation using Load Cell drift, hopper level mismatch, and motor RPM abnormality | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605654 | SEWWANDI C.I it22609531 | 07/03/2026 | 2025-11-15 | 2025-11-20 | false | false | 2025-11-18 | ABEYSEKARA K.S it22605654 |  |  | Boat navigation & Automated feeding
rK7wwU_kjkmn06zx3qKoQ8kAI6QC | Historical feed trend analysis using daily and monthly feeding_history and weight_history aggregates | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605655 | SEWWANDI C.I it22609532 | 07/03/2026 | 2025-11-16 | 2025-11-21 | false | false | 2025-11-19 | ABEYSEKARA K.S it22605655 |  |  | Boat navigation & Automated feeding
JzRKUhZ6NUurwBTyXdrIy8kAJG09 | Real-time feeding monitoring using live feed rate, cumulative grams, and per-minute burn rate | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605656 | SEWWANDI C.I it22609533 | 07/03/2026 | 2025-11-17 | 2025-11-22 | false | false | 2025-11-20 | ABEYSEKARA K.S it22605656 |  |  | Boat navigation & Automated feeding
ZrqqC5Wa3EGWnhc6whejM8kAAB_0 | Feeder health and safety alerting using motor RPM, ESC percent, and motor status | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605657 | SEWWANDI C.I it22609534 | 07/03/2026 | 2025-11-18 | 2025-11-23 | false | false | 2025-11-21 | ABEYSEKARA K.S it22605657 |  |  | Boat navigation & Automated feeding
xXeioDYpmkKVlzkRXmVTtskAIGKl | Boat navigation energy-impact tracking using HC-SR04 ultrasonic sensors, MPU-6050 (angle X/Y), and motor telemetry | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605658 | SEWWANDI C.I it22609535 | 07/03/2026 | 2025-11-19 | 2025-11-24 | false | false | 2025-11-22 | ABEYSEKARA K.S it22605658 |  |  | Boat navigation & Automated feeding
XNhtb17nDkOIfL-mgn7PzckAF0ha | Cross-system operations dashboard combining feeding data (Load Cell + hopper + motor) with boat movement and power usage | Implementation Phase (November 2025 – February 2026) | Not started | Medium | ABEYSEKARA K.S it22605659 | SEWWANDI C.I it22609536 | 07/03/2026 | 2025-11-20 | 2025-11-25 | false | false | 2025-11-23 | ABEYSEKARA K.S it22605659 |  |  | Boat navigation & Automated feeding
B1P1d2LvF0uYdk02azwmq8kAKoeB | Brushless motor setup | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605650 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-08 | 2025-11-12 | false | false | 2025-11-12 | ABEYSEKARA K.S it22605650 |  |  | Boat navigation & Automated feeding
tTGg4_PkSkqi_leaMbb2uMkAGky6 | Motor driver configuration (A4988) | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605651 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-05 | 2025-11-10 | false | false | 2025-11-10 | ABEYSEKARA K.S it22605651 |  |  | Boat navigation & Automated feeding
7OdJX3CdX0mFvwrXB_j8XckAEpG4 | Smart boat mechanical design | Implementation Phase (November 2025 – February 2026) | started | Medium | ABEYSEKARA K.S it22605652 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-11-01 | 2025-11-07 | false | false | 2025-11-07 | ABEYSEKARA K.S it22605652 |  |  | Boat navigation & Automated feeding
v8VH4uTRlEekIVOP2NIxEskAL_n7 | Define testing and evaluation strategy | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605653 | SEWWANDI C.I it22609526 | 07/03/2026 | 2025-10-09 | 2025-10-15 | false | true | 2025-10-15 | ABEYSEKARA K.S it22605653
ERuOgYzah02ke73LOIB0x8kAFlQd | Select machine learning / detection algorithms | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605654 | SEWWANDI C.I it22609526 | 07/03/2026 | 07/10/2025 | 12/10/2025 | false | true | 12/10/2025 | ABEYSEKARA K.S it22605654
cLxF251BsUq9OESFCE3SJckAFYh6 | Design system integration plan | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334 | SEWWANDI C.I it22609526 | 07/03/2026 | 06/10/2025 | 10/10/2025 | false | true | 10/10/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334
7hF5CAT_ukGlE8mHZz3XrckAGBU_ | Design decision-making logic for alerts | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581335 | SEWWANDI C.I it22609526 | 07/03/2026 | 04/10/2025 | 08/10/2025 | false | true | 08/10/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581335
-N6qkWrZs0CI3hGCqzCgyckAOAYw | Create component overview diagram | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581336 | SEWWANDI C.I it22609526 | 07/03/2026 | 02/10/2025 | 07/10/2025 | false | true | 07/10/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581336
lcVSEZN21Umu4oFiHYABDMkAEnxf | Design user notification workflow | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581337 | SEWWANDI C.I it22609526 | 07/03/2026 | 01/10/2025 | 06/10/2025 | false | true | 06/10/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581337
fffWN0oNXkyArC7PMVK3vckAGArs | Design API structure for module communication | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581338 | SEWWANDI C.I it22609526 | 07/03/2026 | 30/09/2025 | 05/10/2025 | false | true | 05/10/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581338
rtGbX0rngUWWpcmU8S0G1skAIB_r | Design database schema for system data | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581339 | SEWWANDI C.I it22609526 | 07/03/2026 | 29/09/2025 | 04/10/2025 | false | true | 04/10/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581339
nWLqH0GrDkOOP_hl206VdskAJedR | Define event-driven alert system architecture | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581340 | SEWWANDI C.I it22609526 | 07/03/2026 | 28/09/2025 | 03/10/2025 | false | true | 03/10/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581340
mKA58FoZFkKx7Zjaxfp6a8kALZYJ | Define sensor integration structure | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581341 | SEWWANDI C.I it22609526 | 07/03/2026 | 26/09/2025 | 30/09/2025 | false | true | 30/09/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581341
pO_1z6w6xEKwx1xz-WR1AckAKxmG | Design cloud communication architecture | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581342 | SEWWANDI C.I it22609526 | 07/03/2026 | 25/09/2025 | 30/09/2025 | false | true | 30/09/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581342
CWCKytEW7EaJqzmenPTrcMkAAwte | Design hardware architecture layout | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581343 | SEWWANDI C.I it22609526 | 07/03/2026 | 24/09/2025 | 29/09/2025 | false | true | 29/09/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581343
P6EgzPZJNUec9kJXL_4-MckADwdy | Define module responsibilities for each team member | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581344 | SEWWANDI C.I it22609526 | 07/03/2026 | 22/09/2025 | 23/09/2025 | false | true | 23/09/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581344
_gjZkHHbV0OubWF7zDv27MkAB5nP | Design complete IoT system architecture | ExecutingDesign & Planning Phase (October – November 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581345 | SEWWANDI C.I it22609526 | 07/03/2026 | 20/09/2025 | 25/09/2025 | false | true | 25/09/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581345
y6asyXw7SUybwJAQngTxaskAE-EG | Apply corrections from panel feedback | Proposal Phase (July – September 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581346 | SEWWANDI C.I it22609526 | 06/03/2026 | 10/09/2025 | 17/09/2025 | false | true | 17/09/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581346
MM6ct62qCE-hCzNNQqz918kAGYJ6 | Conduct proposal presentation | Proposal Phase (July – September 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581347 | SEWWANDI C.I it22609526 | 06/03/2026 | 08/09/2025 | 08/09/2025 | false | true | 08/09/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581347
LbjcuR7yVkmpJh2Nfnkds8kALPUI | Prepare proposal presentation slides | Proposal Phase (July – September 2025) | started | Medium | DILSHAN G H A C it22581334 | SEWWANDI C.I it22609526 | 06/03/2026 | 01/09/2025 | 05/09/2025 | false | true | 05/09/2025 | DILSHAN G H A C it22581334
uSkl5Mf7A0eJYpuaaxuzVMkAO9Xe | Internal proposal review with supervisor | Proposal Phase (July – September 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334 | SEWWANDI C.I it22609526 | 06/03/2026 | 20/08/2025 | 25/08/2025 | false | true | 25/08/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334
zPcts-Wtl0-kUV1T9zJEb8kAMsG3 | Prepare project budget estimation | Proposal Phase (July – September 2025) | started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609526 | 06/03/2026 | 13/08/2025 | 15/08/2025 | false | true | 15/08/2025 | RAJAPAKSHA R.M.K.U it22565358
sx8EqI5RRU6Rh7xe7fkePckAGY7k | Prepare Gantt chart for project timeline | Proposal Phase (July – September 2025) | started | Medium | DILSHAN G H A C it22581334 | SEWWANDI C.I it22609526 | 06/03/2026 | 13/08/2025 | 15/08/2025 | false | true | 15/08/2025 | DILSHAN G H A C it22581334
0mJsXOQT1E-Yg5EjM4VOBMkAI6Vb | Prepare system overview diagrams | Proposal Phase (July – September 2025) | started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609526 | 06/03/2026 | 13/08/2025 | 15/08/2025 | false | true | 15/08/2025 | RAJAPAKSHA R.M.K.U it22565358
bflaqhPjTk-dmqwUCGBRtskABifg | Design high-level system architecture | Proposal Phase (July – September 2025) | started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609526 | 06/03/2026 | 09/08/2025 | 13/08/2025 | false | true | 13/08/2025 | RAJAPAKSHA R.M.K.U it22565358
sELKTY86aUOL7Tp_lpYsIskAPIoV | Define specific research objectives | Proposal Phase (July – September 2025) | started | Medium | ABEYSEKARA K.S it22605634 | SEWWANDI C.I it22609526 | 06/03/2026 | 08/08/2025 | 11/08/2025 | false | true | 11/08/2025 | ABEYSEKARA K.S it22605634
Xr6GaO_PEESbaSKErIRfbMkAJdmt | Define main research objectives | Proposal Phase (July – September 2025) | started | Medium | ABEYSEKARA K.S it22605634 | SEWWANDI C.I it22609526 | 06/03/2026 | 08/08/2025 | 11/08/2025 | false | true | 11/08/2025 | ABEYSEKARA K.S it22605634
GOJJCjqTxU-1bl3erRgFu8kALo0O | Define research problem statement | Proposal Phase (July – September 2025) | started | Medium | RAJAPAKSHA R.M.K.U it22565358 | SEWWANDI C.I it22609526 | 06/03/2026 | 06/08/2025 | 09/08/2025 | false | true | 09/08/2025 | RAJAPAKSHA R.M.K.U it22565358
XXVzZEiRuU6oQjOZREKeVMkAC_ED | Identify research gap in existing aquaculture systems | Proposal Phase (July – September 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334 | SEWWANDI C.I it22609526 | 06/03/2026 | 02/08/2025 | 08/08/2025 | false | true | 08/08/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581334
R1LuZ0-Tf0qP1WVXwC3TyMkAKAqt | Collect and analyze related research papers | Proposal Phase (July – September 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581335 | SEWWANDI C.I it22609526 | 06/03/2026 | 25/07/2025 | 07/08/2025 | false | true | 07/08/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581335
DTWHEKZi8UaxwVK7Q9lDi8kAOt2U | Register project topic in university system | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581336 | SEWWANDI C.I it22609526 | 06/03/2026 | 24/07/2025 | 26/07/2025 | false | true | 26/07/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581336
i4f68LbgdUWkJv4XkSixrskAIXiQ | Prepare Project Charter document | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581337 | SEWWANDI C.I it22609526 | 06/03/2026 | 18/07/2025 | 23/07/2025 | false | true | 23/07/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581337
VVA0qVdrhUugIs6IBxKf9MkAPCqi | Submit Topic Assessment Form | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581338 | SEWWANDI C.I it22609526 | 06/03/2026 | 2025-07-10 | 2025-07-16 | false | true | 2025-07-16 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581338
8OlhLTL0_0-2qqawxb225MkAMI7Z | Prepare Topic Assessment Form (TAF) | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581339 | SEWWANDI C.I it22609526 | 06/03/2026 | 30/06/2025 | 12/07/2025 | false | true | 12/07/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581339
5gMnwknG5U-ojA4yaS2GiMkAK__H | Prepare preliminary project timeline | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581340 | SEWWANDI C.I it22609526 | 06/03/2026 | 24/06/2025 | 26/06/2025 | false | true | 26/06/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581340
hQVF3TXuY0CyRySbhaxcbckABNAC | Define project objectives and expected outcomes | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581341 | SEWWANDI C.I it22609526 | 06/03/2026 | 23/06/2025 | 25/06/2025 | false | true | 25/06/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581341
vHSBNTiJD02wD5yKLxWtXckAFY0Q | Identify required software technologies | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581342 | SEWWANDI C.I it22609526 | 06/03/2026 | 22/06/2025 | 24/06/2025 | false | true | 24/06/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581342
zIiNPYoAgkGgjHXVnr4IVMkAKHFw | Identify required hardware components | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581343 | SEWWANDI C.I it22609526 | 06/03/2026 | 21/06/2025 | 23/06/2025 | false | true | 23/06/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581343
c2XinHNABkiNi5pod-w6lMkAG9tw | Discuss project scope with supervisor | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581344 | SEWWANDI C.I it22609526 | 06/03/2026 | 20/06/2025 | 21/06/2025 | false | true | 21/06/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581344
5swuq1L53Eep94jgjz3MBskAESCE | Form research group and allocate responsibilities | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581345 | SEWWANDI C.I it22609526 | 06/03/2026 | 18/06/2025 | 19/06/2025 | false | true | 19/06/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581345
7yHGh3tVrUWQvVhZD047ackAPHxS | Conduct initial background research on IoT aquaculture systems | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581346 | SEWWANDI C.I it22609526 | 06/03/2026 | 14/06/2025 | 18/06/2025 | false | true | 18/06/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581346
-_ZxODwg1k-E4GpquPQv4ckALpf6 | Identify real-world problems in fish farming | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581347 | SEWWANDI C.I it22609526 | 06/03/2026 | 12/06/2025 | 14/06/2025 | false | true | 14/06/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581347
_qIQ6rJsaUqW1Z85tCSth8kAKbjx | Brainstorming session for aquaculture system idea | Initiating phase (June-July 2025) | started | Medium | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581348 | SEWWANDI C.I it22609526 | 06/03/2026 | 10/06/2025 | 12/06/2025 | false | true | 12/06/2025 | ABEYSEKARA K.S it22605634;RAJAPAKSHA R.M.K.U it22565358;SEWWANDI C.I it22609526;DILSHAN G H A C it22581348
W9PCeE7EI0OcV11Vf_QKv8kANeyY | Submit draft reports | Final Report & Viva (March – April 2026) | started | Medium | SEWWANDI C.I it22609526 | SEWWANDI C.I it22609526 | 30/04/2026 | 2026-06-15 | 2026-06-24 | false | false | 2026-06-24 | SEWWANDI C.I it22609526

## Plan name
Plan name | Koi_Fish_project
Plan ID | _ApvJAyvt0yYg_bEaYsYJckAAa7Y
Date of export | 30/04/2026